## P1800 Timeline
P1850 Timeline for completion and approval by IEEE Standards Association Standards Board
| Task | Duration (days) | Start Date | End Date
Draft Development Phase
| WG chair approves invitation to ballot text | 2 | 2005-03-04 | 2005-03-07
| WG and subcommittees review P1850 draft in preparation for ballot. | 25 | 2005-03-09 | 2005-03-28
| Pre-ballot mandatory editorial coordination for P1850 | 25 | 2005-03-08 | 2005-04-02
| invitation to ballot (30-day process) begins | 30 | 2005-03-08 | 2005-04-07
| sponsor chair approves balance of P1850 ballot group | 4 | 2005-04-08 | 2005-04-11
| technical writer creates P1850 for ballot | 11 | 2005-03-28 | 2005-04-08
| working group chair approves cover letter for P1850 ballot | 2 | 2005-04-08 | 2005-04-11
| technical writer delivers P1850 to IEEE for ballot | 1 | 2005-04-11 | 2005-04-11
Sponsor Ballot
| 30-day initial ballot of P1850 | 30 | 2005-04-12 | 2005-05-12
| ballot summary sent to WG chair / sponsor / Comment file sent to WG chair | 1 | 2005-05-13 | 2005-05-13
| Ballot resolution | 14 | 2005-05-13 | 2006-05-26
| Technical writer prepares P1850 recirculation draft. Secretary prepares ballot comment matrix with dispositions for recirculation. Program manager prepares cover letter to balloters. | 4 | 2005-05-27 | 2005-05-30
WG chair approves cover letter to balloters.
| 10-day recirculation ballot of P1850 / results sent to WG chair / sponsor / program manager | 10 | 2005-05-31 | 2005-06-11
| Program manager creates RevCom submittal package for P1850. WG chair approves and submits RevCom submittal package. | 1 | 2005-06-13 | 2005-06-13
| Press Release: P1850 is submitted to SA Standards Board | 1 | 2005-06-13 | 2005-06-13
| Design Automation Conference |  | 2005-06-13 | 2005-06-17
| RevCom submission deadline | 1 | 2005-08-12 | 2005-08-12
IEEE-SA Standards Board approval
| RevCom approves P1850 | 1 | 2005-09-21 | 2005-09-21
| Standards Board approves P1850 | 1 | 2005-09-22 | 2005-09-22
| IEEE Std 1850-2005 is published | TBD | 2005-09-22 | TBD