## Sheet1
Plan to Complete P1666 Draft LRM by End Nov 2010
| Est time | Start | End
Priorities
(A) Process Control Extensions | 2 weeks | 2010-09-27 | 2010-10-08
(B) Version number macros | 2 weeks | 2010-09-27 | 2010-10-08
(C) Representing the maximum value of sc_time | 1 week | 2010-09-27 | 2010-10-01
(D) sc_event_and_list / sc_event_or_list | 3 weeks | 2010-10-04 | 2010-10-22
(E) Change to sc_port class structure so bind can be overloaded | 3 weeks | 2010-10-11 | 2010-10-29
(F) Review multiple processes writing to the same sc_signal | 2 weeks | 2010-10-18 | 2010-10-29
(G) Add a container class for array-of-port et | 3 weeks | 2010-10-25 | 2010-11-12
(H) Add an sc_pause function. Add an sc_get_status function | 3 weeks | 2010-11-01 | 2010-11-12
(J) Make request_update thread-safe | 2 weeks | 2010-11-08 | 2010-11-19
(K) Naming sc_events | 2 weeks | 2010-11-15 | 2010-11-26
Editorial work e.g. front matter, appendixes |  | 2010-10-04 | 2010-11-26
Other minor technical issues with existing LRM wording |  | 2010-10-04 | 2010-11-26
Draft LRM updated regularly for review |  | 2010-10-04 | 2010-11-26
Review prior to ballot, including iterations |  | 2010-11-29 | 2010-01-14
Start of formal ballot process |  | 2010-01-17
Excluded from the above:
Four controversial/negative issues
Four issues of less concern, including
Minor issues raised by JEITA re. int vs fixed_pt method naming